PROJECT STRATEGY DOCUMENT

Automated Qualified Review Generation System

BRD Analysis & Implementation Planning

Prepared for: bdcode

Date: 13 February 2026

Version: 1.0

CONFIDENTIAL

# Table of Contents

1. Executive Summary

2. Requirement Traceability Matrix

3. Gap & Risk Analysis

4. Implementation Roadmap

5. Resource & Dependency Mapping

6. Assumptions & Constraints

# 1. Executive Summary

## 1.1 Project Overview

The Automated Qualified Review Generation System is designed to streamline the process of capturing high-quality Google Business Profile reviews from satisfied B2B clients. The system transforms manual testimonial collection into an automated workflow that qualifies feedback, generates personalized review drafts using AI, and facilitates client approval before posting.

## 1.2 Business Value

- Increased Review Volume: Reduce friction in the review writing process, leading to higher conversion from satisfied client to published review

- Quality Control: Ensure only highly satisfied clients (rating threshold met) are prompted to leave reviews

- Brand Protection: Internal alerts for low-rated feedback enable proactive customer success intervention

- Marketing Asset Generation: AI-generated drafts serve as reusable testimonial content for case studies and sales collateral

- Compliance: Manual posting requirement ensures adherence to Google Business Profile policies

## 1.3 Key Objectives

- Automate the identification and qualification of high-satisfaction feedback responses

- Generate personalized, authentic-sounding review drafts using AI

- Implement a consent-driven workflow that respects client autonomy

- Create an early warning system for dissatisfied clients requiring intervention

- Achieve zero manual intervention in the qualified feedback to review draft pipeline

## 1.4 Success Metrics

| Metric | Target |
| --- | --- |
| Increase in 4★+ Google Reviews | 25% increase within 6 months |
| Review Conversion Rate | 40% of qualified feedback results in published review |
| Time to Review | Average <72 hours from submission to posting |
| Manual Intervention Rate | 0% for qualified feedback processing |
| Email Delivery Success | >95% successful delivery |

# 2. Requirement Traceability Matrix

## 2.1 Functional Requirements

| ID | Requirement | Priority | Acceptance Criteria |
| --- | --- | --- | --- |
| FR-001 | Calculate average rating from all numeric feedback fields | Critical | Accurate calculation within 1 second |
| FR-002 | Qualify responses meeting threshold (≥8/10 on 10-point scale) | Critical | 100% accuracy in qualification |
| FR-003 | Route low-rated submissions to internal alert system | Critical | Alert sent within 5 minutes |
| FR-004 | Generate AI review draft using client feedback data | Critical | Draft generated within 10 seconds |
| FR-005 | Review draft must be 100-200 words, first-person voice | High | Length and voice validated |
| FR-006 | Include client name, company, service in draft | High | All fields present in output |
| FR-007 | Send consent request email to client | Critical | Email delivered successfully |
| FR-008 | Provide three consent options: Approve, Edit, Decline | Critical | All options functional |
| FR-009 | Support review regeneration with client modifications | Medium | New draft reflects edits |
| FR-010 | Generate Google Business Profile review link | Critical | Link opens correct GBP page |
| FR-011 | Provide copy-to-clipboard functionality for review text | High | One-click copy works |
| FR-012 | Send internal alert for low ratings to Marketing/Sales/HR | High | Correct recipients notified |
| FR-013 | Include client name, rating, feedback summary in alerts | High | All data present in alert |
| FR-014 | Log all edge cases and system events | Medium | Complete audit trail |
| FR-015 | Handle consent non-response after 7 days | Medium | Follow-up or close triggered |

## 2.2 Non-Functional Requirements

| ID | Requirement | Category | Target |
| --- | --- | --- | --- |
| NFR-001 | AI review generation response time | Performance | <10 seconds |
| NFR-002 | Email delivery reliability | Reliability | >95% success rate |
| NFR-003 | System operates within Google ecosystem | Compatibility | Forms, Sheets, Apps Script |
| NFR-004 | Data privacy compliance | Security | GDPR/privacy best practices |
| NFR-005 | Secure handling of client PII | Security | Encrypted storage, access control |
| NFR-006 | System availability | Availability | 99.5% uptime (implied) |
| NFR-007 | Audit logging for compliance | Compliance | Full event logging |
| NFR-008 | No auto-posting to Google Reviews | Compliance | Manual posting enforced |

# 3. Gap & Risk Analysis

## 3.1 Critical Gaps Identified

### Gap 1: Missing Data Fields for AI Generation

Issue: The BRD specifies that AI review generation requires: client name, company name, service used, pain point before engagement, outcome achieved, quantifiable results, and unexpected value. However, the current Client Feedback Form does not capture most of these fields.

Impact: High - The AI cannot generate personalized, context-rich reviews without this input data.

Recommendation: Revise the Google Form to include: Company Name (required), Service/Project Type (dropdown), Primary challenge before engagement (text), Key outcome or result achieved (text), Any unexpected benefits (optional text).

### Gap 2: Missing Client Contact Information

Issue: The form collects LinkedIn profile but does not explicitly capture email address for the consent workflow. While the form shows the submitter's Google account email, this may not be the preferred business contact.

Impact: Medium - Consent emails may go to wrong address or be blocked by spam filters.

Recommendation: Add required field for preferred business email and optional WhatsApp number for multi-channel delivery.

### Gap 3: Rating Scale Inconsistency

Issue: The BRD specifies qualification threshold as "≥4/5 OR ≥8/10" but the feedback form uses only a 10-point scale for all questions. The logic for handling mixed scales is undefined.

Impact: Medium - Ambiguity in threshold calculation could lead to incorrect qualification decisions.

Recommendation: Standardize to 10-point scale only. Define threshold as average score ≥8.0 across all numeric questions, OR overall satisfaction (Q8) ≥8.

### Gap 4: Consent Workflow Conflict

Issue: The form includes Question 9: "May we use your feedback as a testimonial?" which captures initial consent. However, the BRD describes a separate consent workflow for the AI-generated review. The relationship between these two consent mechanisms is undefined.

Impact: Medium - Clients who answer "No" to Q9 should not receive review draft requests, but this logic is not specified.

Recommendation: Define Q9 response as a prerequisite filter. Only proceed to AI generation if Q9 = "Yes" AND rating threshold met.

### Gap 5: Google Business Profile Integration Details

Issue: The BRD mentions generating a "direct review link" to Google Business Profile but does not provide the Place ID or CID needed to construct this URL.

Impact: High - Cannot generate functional review links without business identifier.

Recommendation: Document the Google Place ID or CID for bdcode's GBP listing. Store as configuration parameter.

### Gap 6: Undefined AI Model and Prompt Structure

Issue: The BRD references "AI API (OpenAI or equivalent)" without specifying which model, prompt engineering approach, or fallback strategy.

Impact: Medium - Inconsistent outputs, potential cost overruns, or service interruptions.

Recommendation: Specify primary model (e.g., GPT-4, Claude), define structured prompt template, implement retry logic and fallback model.

## 3.2 Risk Register

| ID | Risk Description | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R-001 | AI generates generic/robotic reviews | Medium | High | Use structured prompts with specific context; implement human review for first 20 outputs |
| R-002 | Low client approval rate for drafts | Medium | Medium | A/B test tone variations; offer easy edit mechanism |
| R-003 | AI API service disruption | Low | High | Implement fallback to secondary API; queue mechanism for retry |
| R-004 | Policy violation accusation from Google | Low | Critical | Strict manual posting only; no incentive offers; document compliance |
| R-005 | Email deliverability issues | Medium | Medium | Use verified sending domain; implement WhatsApp backup channel |
| R-006 | High rating but negative written feedback | Low | Medium | Implement sentiment analysis on open-ended responses as secondary filter |
| R-007 | Data privacy breach | Low | Critical | Encrypt PII; implement access controls; regular security audits |
| R-008 | Client significantly modifies AI draft before posting | Medium | Low | Accept as desired behavior; consider capturing final text for records |
| R-009 | Multiple submissions from same client | Low | Low | Implement deduplication logic based on email; take most recent |
| R-010 | Scope creep into Phase 2 features | Medium | Medium | Strict change control; defer to Phase 2 backlog |

## 3.3 Edge Cases Requiring Clarification

| ID | Edge Case | Current State | Recommended Handling |
| --- | --- | --- | --- |
| EC-01 | High numeric rating but negative open-text feedback | Not addressed | Run sentiment analysis on Q10; flag for human review if negative |
| EC-02 | Low numeric rating but positive open-text feedback | Not addressed | Still trigger internal alert; include positive comments in alert |
| EC-03 | Client clicks Approve but never posts review | Not addressed | Send one follow-up reminder after 7 days; no further action |
| EC-04 | Client requests unlimited edits to draft | Not addressed | Cap regeneration at 3 attempts; offer manual support path |
| EC-05 | Form submitted with all 10s but Q9 = No | Not addressed | Do not generate review draft; log as missed opportunity |
| EC-06 | Client submits form multiple times | Not addressed | Process only latest submission per email; archive previous |
| EC-07 | AI generates review outside 100-200 word range | Not addressed | Implement validation; regenerate if out of bounds |
| EC-08 | Client email bounces | Not addressed | Attempt WhatsApp if available; flag for manual outreach |
| EC-09 | Consent timeout (no response in 7 days) | Mentioned but undefined | Send single reminder at day 5; close case at day 7 |

# 4. Implementation Roadmap

## 4.1 Phase 1: Design & Planning (Weeks 1-2)

Objectives: Finalize requirements, resolve gaps, design system architecture

| Deliverable | Owner | Success Criteria |
| --- | --- | --- |
| Revised Google Form with all required fields | Product Owner | All data fields for AI generation included |
| Finalized rating qualification algorithm | Business Analyst | Clear logic documented and approved |
| Google Business Profile Place ID documented | Marketing | Valid review link generated |
| AI prompt engineering specification | AI Engineer | Prompt template producing quality outputs |
| System architecture diagram (Option A or B) | Solution Architect | Approved by technical stakeholders |
| Email template designs (consent request, approval) | Marketing/UX | Templates approved by stakeholders |
| Internal alert notification design | Product Owner | Recipients and content defined |
| Data flow and privacy documentation | Security/Compliance | GDPR compliance confirmed |

## 4.2 Phase 2: Development (Weeks 3-5)

Objectives: Build core automation, integrations, and AI pipeline

| Deliverable | Owner | Success Criteria |
| --- | --- | --- |
| Google Sheets data capture pipeline | Developer | Form responses automatically logged |
| Rating calculation and qualification logic | Developer | Accurate threshold determination |
| AI API integration (OpenAI/Claude) | AI Engineer | API calls returning valid responses |
| Review draft generation function | AI Engineer | Drafts meet quality requirements |
| Consent email automation | Developer | Emails sent within 5 minutes of qualification |
| Consent response handler (Approve/Edit/Decline) | Developer | All paths functional |
| Final review delivery with copy button and GBP link | Developer | One-click copy working |
| Internal alert system for low ratings | Developer | Alerts delivered to correct recipients |
| Edge case handling and logging | Developer | All EC scenarios handled |
| Error handling and retry mechanisms | Developer | Graceful failure with logging |

## 4.3 Phase 3: Testing (Weeks 6-7)

Objectives: Validate all functionality, quality, and edge cases

| Test Type | Scope | Success Criteria |
| --- | --- | --- |
| Unit Testing | Individual functions (rating calc, AI call, email) | 100% of critical paths pass |
| Integration Testing | End-to-end form submission to email delivery | Complete workflow executes correctly |
| AI Output Quality Testing | Review 50+ generated drafts for quality | >90% meet tone and length requirements |
| Edge Case Testing | All scenarios in EC table | Each edge case handled as specified |
| Performance Testing | AI response time, email delivery speed | <10 sec AI response, >95% email success |
| User Acceptance Testing | Marketing/Sales team validates workflow | Sign-off from all stakeholders |
| Security Testing | PII handling, access controls | No vulnerabilities identified |

## 4.4 Phase 4: Deployment & Launch (Week 8)

Objectives: Go live with controlled rollout and monitoring

| Activity | Owner | Success Criteria |
| --- | --- | --- |
| Production environment setup | DevOps/Developer | All services running in production |
| Soft launch with 10 real clients | Marketing | End-to-end validation in production |
| Monitoring dashboard setup | Developer | Real-time visibility into pipeline |
| Team training session | Product Owner | All stakeholders understand workflow |
| Documentation handover | All | Runbook and troubleshooting guide complete |
| Full launch announcement | Marketing | System available for all clients |
| Post-launch review (Week 10) | Product Owner | KPIs reviewed and adjustments planned |

# 5. Resource & Dependency Mapping

## 5.1 Required Skills & Roles

| Role | Responsibilities | Allocation | Duration |
| --- | --- | --- | --- |
| Product Owner | Requirements clarification, stakeholder alignment, UAT coordination | 50% | 8 weeks |
| Google Apps Script Developer | Build automation in Google ecosystem, email integration, data processing | 100% | 5 weeks |
| AI/ML Engineer | Prompt engineering, API integration, output quality tuning | 75% | 4 weeks |
| UX Designer | Email templates, consent UI, review delivery page | 25% | 2 weeks |
| QA Engineer | Test planning, execution, edge case validation | 75% | 3 weeks |
| Marketing Stakeholder | Form design input, email copy, quality review | 10% | 8 weeks |
| Security/Compliance Reviewer | Privacy review, data handling approval | 10% | 2 weeks |

## 5.2 Technology Stack

| Component | Technology | Purpose |
| --- | --- | --- |
| Form Platform | Google Forms | Client feedback collection |
| Data Storage | Google Sheets | Response storage and processing |
| Automation Engine | Google Apps Script OR Zapier/Make | Workflow orchestration |
| AI Service | OpenAI API (GPT-4) or Anthropic API (Claude) | Review draft generation |
| Email Delivery | Gmail API or SendGrid | Consent and delivery emails |
| Notification (optional) | WhatsApp Business API or Twilio | Backup delivery channel |
| Logging | Google Sheets or Cloud Logging | Audit trail and debugging |
| Review Link | Google Business Profile URL | Direct posting link |

## 5.3 External Dependencies

| Dependency | Provider | Risk Level | Mitigation |
| --- | --- | --- | --- |
| AI API availability | OpenAI/Anthropic | Medium | Implement fallback provider |
| Google Forms/Sheets uptime | Google Workspace | Low | Google SLA covers availability |
| Email deliverability | Gmail/SendGrid | Medium | Use verified domain, monitor bounces |
| Google Business Profile access | Google | Low | Maintain admin access |
| Client email responsiveness | Clients | High | Multi-channel delivery option |
| API rate limits | All providers | Low | Implement queuing and backoff |

## 5.4 Budget Considerations

| Item | Estimated Cost | Notes |
| --- | --- | --- |
| AI API usage (OpenAI GPT-4) | $50-150/month | ~500 reviews/month at ~$0.10-0.30 each |
| Google Workspace | Existing | Already in use |
| Zapier/Make (if Option B) | $0-50/month | Free tier may suffice initially |
| SendGrid (if not Gmail) | $0-20/month | Free tier for low volume |
| WhatsApp Business API | $0-25/month | Usage-based pricing |
| Development effort | 40-60 hours | Internal or contractor |

# 6. Assumptions & Constraints

## 6.1 Assumptions

- Google Workspace Access: bdcode has an active Google Workspace subscription with access to Google Forms, Sheets, and Apps Script.

- AI API Budget: Budget is approved for ongoing AI API costs (estimated $50-150/month based on volume).

- GBP Admin Access: Marketing team has admin access to the Google Business Profile for bdcode.

- Client Email Validity: Clients submitting feedback will provide valid, monitored email addresses.

- Form Revision Authority: Product Owner has authority to modify the Google Form to add required fields.

- Single Business Location: Phase 1 targets a single Google Business Profile location. Multi-location routing is deferred to Phase 2.

- B2B Context: All feedback respondents are B2B clients with professional context and expectations.

- English Language: All communications and reviews are in English. Multi-language support is out of scope.

- Voluntary Posting: Clients will voluntarily post approved reviews without requiring incentives (compliant with Google policy).

## 6.2 Constraints

- Google Policy Compliance: System must not auto-post reviews to Google Business Profile. All reviews must be manually submitted by clients.

- No Review Incentives: System must not offer rewards, discounts, or incentives in exchange for positive reviews (Google ToS violation).

- Google Ecosystem: Solution must operate within Google ecosystem for data collection and storage (Forms + Sheets).

- Data Privacy: Client PII must be handled securely and not shared without explicit consent.

- Consent Required: No AI-generated content may be used without explicit client approval through consent workflow.

- Manual Intervention Target: System must achieve zero manual intervention for qualified feedback processing; exceptions only for edge cases.

- Performance SLAs: AI generation must complete in <10 seconds; email delivery success must exceed 95%.

- Phase 1 Scope: Features explicitly marked as Phase 2 (NPS dashboard, testimonial cards, LinkedIn drafts, case study generation, multi-location routing, sentiment dashboard) are out of scope.

## 6.3 Decisions Required Before Development

| ID | Decision Item | Options | Decision Owner |
| --- | --- | --- | --- |
| D-001 | Architecture approach | Option A (Apps Script) vs Option B (Zapier/Make) | Technical Lead |
| D-002 | AI provider selection | OpenAI GPT-4 vs Anthropic Claude vs Other | AI Engineer + Budget Owner |
| D-003 | Rating threshold definition | Average ≥8 vs Overall Q8 ≥8 vs Both | Product Owner |
| D-004 | Email delivery method | Gmail API vs SendGrid vs Other | Developer |
| D-005 | Backup notification channel | Include WhatsApp or email-only | Product Owner |
| D-006 | Internal alert recipients | Marketing + Sales + HR or subset | Product Owner |
| D-007 | Consent timeout handling | Auto-close vs send reminder vs escalate | Product Owner |
| D-008 | Edit regeneration limit | Unlimited vs capped at N attempts | Product Owner |

# Appendix A: Proposed Form Field Additions

Based on Gap Analysis, the following fields should be added to the Client Feedback Form:

| Field Name | Type | Required | Purpose |
| --- | --- | --- | --- |
| Your Full Name | Short text | Yes | Personalize review attribution |
| Company Name | Short text | Yes | Include in review context |
| Preferred Email for Follow-up | Email | Yes | Consent workflow delivery |
| WhatsApp Number (optional) | Phone | No | Backup delivery channel |
| Service/Project Type | Dropdown | Yes | Context for AI draft |
| Main challenge before working with us | Long text | Yes | Pain point for AI draft |
| Key result or outcome achieved | Long text | Yes | Outcome for AI draft |
| Any measurable results (optional) | Short text | No | Quantifiable claims for AI draft |
| Unexpected benefit or bonus value | Long text | No | Additional positive content |

# Appendix B: Proposed AI Prompt Structure

The following structured prompt template is recommended for review generation:

SYSTEM:

You are a professional copywriter helping B2B clients write authentic Google Business Profile reviews. Generate a review draft that:

- Is 100-200 words

- Uses first-person voice (client perspective)

- Sounds natural and authentic, not robotic or generic

- Has a professional B2B tone

- Avoids keyword stuffing and exaggerated claims

- Is suitable for Google Business Profile

USER:

Write a review for [COMPANY: bdcode] from the perspective of:

- Client Name: {client_name}

- Company: {company_name}

- Service Used: {service_type}

- Challenge Before: {pain_point}

- Outcome Achieved: {outcome}

- Measurable Results: {results_if_any}

- Unexpected Value: {bonus_if_any}

- Overall Rating: {average_score}/10

— End of Document —